## Slide 1: PJ Garuda Execution Phase Proposal (PMO/FA Additional) (May 2026 – Jul 2026)
2026年4月17日
株式会社 三菱UFJ銀行 御中

## Slide 2: 目次 (Agenda)
背景・目的 (Background / Purpose)
ご支援概要 (Approach)
体制案 (Team Structure)
報酬価格 (Commercials)
統合支援実績 (Value Proposition)

## Slide 3: 目次 (Agenda)
背景・目的 (Background / Purpose)
ご支援概要 (Approach)
体制案 (Team Structure)
報酬価格 (Commercials)
統合支援実績 (Value Proposition)

## Slide 4: Our Understanding
Propose support for the Execution Phase in PMO and FA Support.
1. Background / Purpose
Background
At the Steering Committee and Executive Management Meeting in March 2026, it was agreed to move the project into the Execution Phase. Based on this, our understanding is that detailed execution planning will be done between April and July 2026.
Detailing of the Execution Plan – the key objective is to refine project costs and finalize the master schedule prior to the Executive Management Meeting in July.
Establishment of the Execution Phase structure – A voluntary disclosure is being planned for May. Following this, the project will shift to a structure that involves all employees of JKT Branch and BDI. In addition, from June, communications to customers and obtaining consent will commence. The project will move into a full-fledged Execution Phase structure involving both internal and external stakeholders.
Proposed Support
We propose the following PMO/FA support for the Execution Phase from April 2026 to July 2026.
❶ PMO Support Overall PMO：Support the formulation of various execution plans and the establishment and ramp-up of the project structure toward the Executive Management Meeting in July.
Local PMO Support：Based on the above overall direction, support the operation of WGs/FGs and the management of progress and issues.
❷ FA Support Support the preparation of documents to be submitted to the authorities and internal coordination items related to the integration. Drive the delisting plan and detail out the operation and liquidation plan for remaining assets.
不変

## Slide 5: 目次 (Agenda)
背景・目的 (Background / Purpose)
ご支援概要 (Approach)
体制案 (Team Structure)
報酬価格 (Commercials)
統合支援実績 (Value Proposition)

## Slide 6: Timeline PMO
Below are the PMO High Level Timeline.
2. ご支援概要 (Approach)
 |  | FY2025 |  |  |  |  | FY2026 |  |  |  |  |  |  |  |  |  |  |  | FY2027 |  |  |  | 
 |  | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
 | Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Integration Plan / Regulatory Negotiations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Business and Operation Design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Communications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Organization and Facility |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Transition Preparation (Training, UAT) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
▼ [Tentative]
Day 1
5th Steering Committee
▼
▼ Executive
Management
Meeting
Integration Planning Period (Planning Phase)
6th Steering Committee
▼
9th Steering Committee
▼
8th Steering Committee
▼
7th Steering Committee
▼
BoC /
BoD (BDI) ▼
Voluntary Announcement ▼
Official Public Disclosure ▼
▼ BDI Shareholders’ Meeting
▼ Executive
Management
Meeting
Integration Execution Period (Execution Phase)
* Including platform (segmentation, credit rating) and Tail Management operations.
Transition Preparation Period (Execution Phase)
Final Decision
Identify key changes for the execution phase
Define WBS and
Schedule
Detail New Banking Operations and Processes*
Update Procedure, Manuals and Rules
Prepare for Integration Transition
Design Organization and HR Schemes <HR>
Design Detailed Organization Structure <each WG>
Develop Training Plan
Execute Training
Plan and Prepare UAT
Execute UAT
Prepare for Voluntary Announcement
Customer Explanation and Consent Acquisition / Internal Communications
Plan for Re-location and Vendor Arrangements <PMO>
Detail Migration Tasks and Operational Design for Locations
Prepare Integration Plan Draft
Pre‑negotiation on Integration Plan and Detail Integration Content
1st Finalization
2nd Finalization
Final Version
Formulate Next‑Fiscal‑Year Plan and Cascade to WG (subject to further discussions)
Define KPI <Each WG>
Prepare for Public Disclosure
不変

## Slide 7: Timeline FA - Structure
Below are the FA High Level Timeline.
2. ご支援概要 (Approach)
Milestone
LD1
5th Steer Co.
Executive
Management
Meeting
2026
2027
Integration Plan Approval
Executive
Management
Meeting
Voluntary
Announcement
BDI Shareholders’
Meeting
Regulatory
Reporting
Pre-consultation for integration
Integration
Liquidation
(Integration-related only)
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Jan
Migrate
Decision
Integration Structure
OJK briefing / high-level
alignment
OJK
Auditing
Integration
Announcement
Prepare Integration
Plan Skeleton (HHP)
Define
Roles and
Responsibilities
HQ/JKT/BDI review
and Finalization
Adjustment based on OJK consultation
Handle Creditor
Objection
Procedures
Send notice
for BDI EGMS
Draft Conditional
Integration
Agreement (CIA)
Execute CIA
KJPP
Valuation
Calculate number
of BDI shares to
be issued
Pre-consultation with KJPP / external auditor
Prepare and finalize
regulatory submission
materials for integration
Issue
Integration
Certificate
Obtain approval
for amendment
of Articles
of Association
Amend BDI Articles
of Association
Review and finalize BDI Articles of Association (HQ / JKT / BDI)
Consultation
points
Wrapping up
Tail Assets
Assess pre-LD1
reduction approach
Transfer / Tail Assets
OJK briefing / agreement
Agree on execution
plan and schedule
for pre-LD1
Reduction
Execute pre-LD1 reduction / DBF pre-alignment
Capital
Increase
Delisting Scenario
Confirmation
Approach for Delisting?
Define terms for rights issue (assuming listing maintained)Prepare prospectus skeleton
(If listing is maintained)
Finalize prospectus
(If listing is maintained)
Execute rights issue※
JKT Branch
FY2026 FS Confirmation
Assess financial impact and
regulatory ratio compliance
Develop detailed execution
plan for rights issue※
※After confirming the delisting scenarios, the execution timing will be decided
FY2026
FS
Confirmation
Regulatory
Submission
Planning /
Role Definition
Update
Business
plan
OJK
Approval
不変

## Slide 8: Timeline FA – Delisting
Below are the FA High Level Timeline.
2. ご支援概要 (Approach)
▼Ref: 8/2 LD1
▼Ref: 3/31 Submission of Integration Plan
2026
Mar
Apr
May
June
July
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
June
July
Aug
2027
Milestone
Delisting
Timeline
▼3/23 MUFG Mgmt MTG
▼3/31 BDI AGMS
▼7/6 BDI EGMS
▼7/20 Absence
Procedure Completion
▼7/20 Revocation Request to OJK
▼Early Apr: Voluntary Disclosure (Delisting/Integration)
▼BDI Stock Trading Halt
Preparation for EGMS (3 months)
VTO Period (4 Rounds: 4.5 months)
▼VTO Completion
Shareholder Outreach/Absence Evidence Collection
▼4/1 Submit Delisting/EGMS Agenda to OJK
▼6/19 EGMS Invitation
Delisting Plan Submission
Voluntary Disclosure
Shareholder Approach (for 3 months)
▼7/13 VTO Statement to OJK/Announcement
▼7/28 VTO Statement Effective
▼Report VTO Completion to OJK
Absence Procedures (6 months)
Absence Application to District Court
Court Stipulation
Transfer of Shares to BHP
Stakeholder Exemption
Delisting Approval
▼8/23 Delisting
Completion
▼Ref: 6/15 EGMS
不変

## Slide 9: Timeline FA – Tail Management
Below are the FA High Level Timeline.
2. ご支援概要 (Approach)
Milestone
LD1
5th SteerCo
Mgmt MTG
2026
2027
Integration Plan Approval
Mgmt MTG
Voluntary
Announcement
BDI EGMS
Regulatory
Negotiation
Tail Operations
Tail Liquidation
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Jan
Transition
Decision
Discuss/Align on Remaining Assets Minimization Approach
Align on Minimization Timeline/Execution Approach
(before LD1)
Create BRD for Tail Requirements
Define Scope for Tail Reporting/
Regulatory Negotiation
Confirm Regulatory Requirements for Tail Reporting (OJK)
Negotiate/
Agree on Remaining Assets
Define Scope
for Tail Operations
Define Detailed Operation
Flows of Tail Operations
Create Resource Plan for
Tail Operations (by names)
Update Manuals/
Prepare for Trainings
Conduct UAT
Execute Minimization Approach
Draft Revocation Preparation Approval Documents (1st Draft)
Draft Revocation Preparation Approval Documents (2nd Draft)
Draft Revocation Preparation Approval Documents (Final Draft)
Pre-Consultation for Integration
Finalize Integration Plan (Settlement of Remaining Obligation Sections)
Create Integration Plan (Settlement of Remaining Obligation Sections)
Follow-up Discussions
Operation Transition/
Rehearsal
Finalize FS
of FY2026
FY2026 Corporate
Tax Filing
Receive Tax Letter
From DGT
Follow-up Discussions for Integration
Pre-Consultation for Revocation
Resourcing
Operations
System
Create UAT Approach/Migration Policy
Conduct Trainings/
Prepare for Operation Migration
Create UAT Plan/Migration Plan
HR Announcement/
Internal Adjustments
Preparation
Manual
Migration
ITb Preparation
Conduct ITb
不変

## Slide 10: Key Tasks and Resourcing PMO
2. ご支援概要 (Approach)
Below are the key activities supported by Accenture PMO team from Apr-2026 to Jul-2026.
②-2.FG Support
②-1.WG Support
①.Overall PMO Support
<Apr-2026 to Jul-2026>
Local: 5
Lead×1
WG/FG PICs×4
<Apr-2026 to Jul-2026>
HQ: 4
Lead×1
WG/FG PICs×3
②Local PMO Support
Category
FG progress management and organizing individual topics for discussion
Progress/Issue/Risk management by FG⇒ Integration Structure/Tail, Communications, Branding, Location, Customer Handling, Contract Migration, Regulatory Reporting
Support to organize specific topics in each FG
Overall project operation and management
Progress/Issue/Risk Management, various coordination
Including change management
Support for Integration Plan documents
Preparation of Overall Migration Plan, Migration Rehearsal Plan
Preparation of Migration Checklist
Preparation of UAT Execution Plan etc
WG progress management and organizing individual topics for discussion
Progress/Issue/Risk management by WG⇒① Overall program management (including management report) . ② PICs will be assigned to each WG for Progress/Issue/Risk management
Support to organize specific topics in each WG ⇒ Main areas of support are in Corporate Banking, Operations, Treasury, Transaction Banking
Tasks
Resource
JPN
IDN
不変

## Slide 11: Key Tasks and Resourcing FA
2. ご支援概要 (Approach)
Below are the key activities supported by Accenture FA team from Apr-2026 to Jul-2026.
Structure
Delisting ・ Going-Private
Overall transaction project management
Integration & Capital structure execution support
Update business plan, valuation and communication with independent appraiser
Manage communications with securities firms and project management of delisting
Define detailed steps for VTO under going-private scheme
Minority shareholder communication support
Tail Management execution support
In particular, support for organizing the key issues and assisting with consideration from the perspective of manual migration in Tail Management.
Prepare liquidation plan document and support regular communication with regulators
Define processing policies for liquidation, transfer, termination, or sale from financial perspective
Tail Management
N/A
<Apr-2026 to Jul-2026>
HQ: 4
Lead×1
Member× 34
JPN
IDN
変更
（赤字）
Additional member

## Slide 12: 目次 (Agenda)
背景・目的 (Background / Purpose)
ご支援概要 (Approach)
体制案 (Team Structure)
報酬価格 (Commercials)
統合支援実績 (Value Proposition)

## Slide 13: Team Structure（案） – PMO（2026年5月～2026年7月）
3. 体制案 (Team Structure)
Client Account Lead
Ippei Hayakawa (Financial Service Managing Director)
Advisors
Hindriasari, Tri (P) (Financial Service Managing Director)
Hideyuki Kitabatake (P) (Financial Service Managing Director)
[Indonesia]
Project Executive
Anggraini, Tari S. (P)
(Financial Service Managing Director)
PMO Lead
Muhandri, Narendi(F) (Strategy & Consulting Manager)
Cross Entity IT-PMO Lead
Thio, Moreyn Intan Ireine(F) (Technology Consulting Senior Manager)
Manager(F)×3
Staff (F)*
*Jun-2026~ Jul-2026
IT-PMO
Kohbuchi (F)
Manager(F)
Staff (F)
Staff (F)
PMO
[Japan]
Project Lead
Project Executive
Shingo Yamamoto (Strategy & Consulting Managing Director)
Ryosuke Fujihara (P)
(Strategy & Consulting Principal Director)
Shozo Kubo (P) (Technology Consulting Associate Director)
Timothy (F)
Staff (F)
System/IT
Staff (F)
Staff (F)
Staff (F)
Staff (F)
PMO
Okumura (P)
Manager(F) Manager(F)
Staff (F)
Staff (F)
PMO（FA）
Project Lead
TBC (F)
Staff (F)×5
Functional
Support
変更
（赤字）

## Slide 14: 目次 (Agenda)
背景・目的 (Background / Purpose)
ご支援概要 (Approach)
体制案 (Team Structure)
報酬価格 (Commercials)
統合支援実績 (Value Proposition)

## Slide 15: Commercials – JP PMO/FA Additional
前ページ記載の弊社体制において、下記期間で費用を算定した結果を以下の通り御案内させていただきます。
4. 報酬価格 (Commercials)
＜前提条件、支払方法等＞
  プロジェクトの開始は、貴行・弊社間の契約締結後となります。開始日が変更になった場合には、終了期日も同じく変更となります。
  プロジェクトメンバーについては、弊社内の会議・研修等に参加する場合、プロジェクトを不在にする場合がございます。
  現時点では再委託は想定しておりませんが、弊社子会社のメンバーが参画する場合は、貴行の了解を得る予定です。
  プロジェクト期間中に当初予期されない事情や、前提条件の変更が発生し、報酬見積り額に差異が生じることが明らかになった場合には、事前にご相談させて頂きます。
  弊社から貴行への報酬支払請求は、各月末ご請求、翌月末お支払いとさせていただきます。
  なお、本件はコンサルティング業務であり、契約の形態は「準委任契約」とさせて頂きます。瑕疵担保責任(契約不適合責任)が発生しないことを前提としております。
  その他、契約内容の詳細は、契約書締結時にご確認させて頂き、契約書に記載致します。
  本委託業務の実施にあたり、貴行・弊社間で個人情報、仮名加工情報、匿名加工情報、個人関連情報（いずれも用語の定義については、個人情報の保護に関する法律（平成１５年法律第５７号）の定義に従う。）の授受の想定はありません。
  本業務には、監査業務、会計業務、投資銀行業務、法務、税務その他の規制対象の業務は含まれないものと致します。
  貴行は、本業務に関して自らに適用される法令の遵守およびその解釈について責任を負うものとし、弊社は、当該法令の遵守およびその解釈について責任を負いません。
  貴行は本業務の内容（提出物等の本業務の遂行の結果を含む）を自己の意思と責任において評価のうえ使用するものとし、弊社はいかなる場合も貴行その他第三者による本業務の内容の使用の結果について責任を負いません。
  弊社は第三者の製品および作業について責任を負いません。
  貴行にて、当社の本業務の遂行にあたり、自己の責任で、必要なデータやプログラムのバックアップを確保をお願い致します。データの喪失・破損について、当社は責任を負わないものと致します。
  貴行が弊社に提供する本業務の遂行に必要な資料もしくは情報の提供の懈怠、遅延もしくは誤り、協力の拒否、または分担作業の不完全な履行等貴行の責に帰すべき事由のために本業務の進捗またはその内容に支障が生じたときは、弊社は、これらに対して責任を負いません。
  弊社メンバーの作業場所としては貴行オフィスまたはリモートワーク環境（作業員の自宅）を想定しております。
取組み概要
報酬価格（税抜）
期間
PJ Garuda Execution Phase – JP (PMO/FA Additional)
14,700,000
2026年05月07日-2026年7月31日
新規

## Slide 16: 目次 (Agenda)
背景・目的 (Background / Purpose)
ご支援概要 (Approach)
体制案 (Team Structure)
報酬価格 (Commercials)
統合支援実績 (Value Proposition)

## Slide 17: 統合支援実績＜国内＞
弊社は、国内金融機関の統合案件において、全体PMO等のプロジェクト管理の支援をしております。
5．統合支援実績
クライアント
弊社支援内容
証券会社 合併
証券
全体PMOとして合併後のビジネスモデルの検討、合併計画として取りまとめ、Day1までの推進を支援
IT領域における開発全体PMO、個別システムのPMOを担当
証券会社 合併
保険
経営企画部直下の統合委員会事務局において、全体PMOを支援（統合計画の策定、経営報告等）
事務及びIT分科会の全体PMO、IT子会社の開発PMOを担当
証券会社
合併
メガバンクにおける
グローバル
業務統合
全体PMO支援の役割において、グローバル全体のプロジェクト管理方針・計画の策定、Day1までの推進を支援
メガバンク
合併
銀行
海外系システムのシステム統合領域において、個別システムのPMOとしてDay1までの推進を支援
都市銀行の
合併
全体PMO支援の役割において、プロジェクト管理方針・計画の策定、テスト計画・移行計画策定、経営層意思決定を支援
プロジェクト概要
メガバンク系証券会社2社におけるグループ内統合にかかるプロジェクト
メガバンク系証券会社2社におけるグループ内統合にかかるプロジェクト
メガバンク系グループ会社におけるグローバルでの市場系部門の業務再編プロジェクト
メガバンクの2社合併にかかるプロジェクト
都市銀行の2社合併にかかるプロジェクト
全体計画 策定支援
個別領域 推進支援
全体PMO 管理支援
損保系生保
合併
経営企画部直下の合併支援室において、全体PMOを支援（全体管理計画の策定、PJT推進管理）
IT領域における開発全体PMO・個別システムPMOを担当
日系の大手損害保険会社同士の2社合併にかかるプロジェクト
合併全体事務局、事務・IT専門部会および横断移行PTに関するDay1までの計画策定・推進を支援
メガバンクグループ証券会社 2社におけるグループ内合併にかかるプロジェクト
不変

## Slide 18: 統合支援実績＜海外（アジア）＞
ご支援の内容は「計画」および「実行」が最も多く、本プロジェクトにおいて各社ご支援の経験・ノウハウを活かすことが可能です。
5．統合支援実績
MERGER | COUNTRY | YEAR INTEGRATION STARTED | Accenture Involvement |  |  | 
 |  |  | Due Diligence | Integration Planning | Integration Execution | Post Deal
DBS / ANZ | 6 ASIAN countries | 2016 |  |  |  | 
DBS / Societe Generale |  | 2014 |  |  |  | 
BTMU / Bank of Ayudhya |  | 2013 |  |  |  | 
RHB / OSK | 5 ASEAN countries | 2013 |  |  |  | 
CIMB / RBS Securities Asia | 9 ASIAN countries | 2012 |  |  |  | 
DBS / Danamon |  | 2012 |  |  |  | 
OCBC / Keppel TatLee |  | 2012 |  |  |  | 
ANZ / RBS | 6 ASIAN countries | 2009 |  |  |  | 
CIMB / Bank Thai |  | 2008 |  |  |  | 
MERGER | COUNTRY | YEAR INTEGRATION STARTED | Accenture Involvement |  |  | 
 |  |  | Due Diligence | Integration Planning | Integration Execution | Post Deal
Niaga / Lippo |  | 2008 |  |  |  | 
CIMB / SBB |  | 2006 |  |  |  | 
Bank Permata (5 banks) |  | 2002 |  |  |  | 
AmBank / AmFinance |  | 2002 |  |  |  | 
UOB / OUB |  | 2001 |  |  |  | 
Alliance Bank (7 institutions) |  | 2001 |  |  |  | 
Maybank / Phileo Allied |  | 2000 |  |  |  | 
Mandiri (4 banks) |  | 1999 |  |  |  | 
RHB / DCB / Kwong Yik |  | 1997 |  |  |  | 
不変

## Slide 19: ACCENTURE JOURNEY WITH DANAMON
Danamon S&D Regional Structure Design and Branch Optimization
(2015)
Danamon Data & Analytics Blueprint
(2017)
2015
2013
Danamon Procurement Operating Model
(2013)
2019
Our Principles of Working with Danamon
Collaborative: We worked collaboratively to deliver outcomes and complement BDI internal capabilities
Intimate Knowledge of BDI: Strong understanding of BDI ways of working
Right Team: We provide a team with the right experience and balanced business & IT capabilities
Value Creation: We relentlessly focus on value creation
Pragmatic Approach: We provide practical solutions, based on our experience, tailored to BDI’s context
Rigour and Structure: We help instil the methodologies, mind-set and capabilities required to execute
Global Leading Practice: We connect globally, internally and externally, to bring you leading practices
Group Wide, SEMM, Adira Synergy, Finance & HR Operating Model
(2014)
Adira Transformation Implementation and ACCTION Assessment
(2017)
Adira Cust. Retention & Loyalty
(2019)
Adira Customer Experience Blueprint
(2018)
Danamon Enterprise & Data Analytics Planning
(2014)
Adira Next Gen Biz. Model
(2015)
BDI – BNP Merger & Post Merger Sales Model
(2019)
Adira BPR Acquisition
(2020)
Danamon Security Review
(2021)
Adira Data - Driven
(2022-2023)
2021
5．統合支援実績
不変

## Slide 20: 貴行へのご支援実績（PMO含む）
弊社は貴行における企画検討支援～実行におけるPMO支援まで数多くのプロジェクトのご支援実績があります。
5．統合支援実績
貴行へのご支援実績
ビジネスコンサルティング
テクノロジー
オペレーション
サービス提供種類:
現在ご支援中案件
システム
法人・リテール
ウェルスマネジメントデジタルプラットフォーム構築
法人契約電子化（DocuSign）
海外事務集中プロジェクト
コーポレートバンキング・国際業務
財務企画部BPR
財務・コンプライアンス・リスク
AML全行アセスメント対応
FCCデータガバナンスプロジェクト
市場系MiFID2対応プロジェクト
市場
システム本部中計戦略策定
システム
海外コアバンキングシステム導入（T24、インド/香港）
DI推進部支援（RPA/Blockchain等)
AMLシステム開発（OTUS、Actimize）
住宅ローン業務自動化（PEGA）
事務センター間連携システム導入（PEGA）
GFCDテクノロジープログラム（G-COP導入）
コンプライアンス
全行アーキテクチャ戦略推進
（CRM・商品改廃・事務・データ標準化等）
全社横断
市場系アーキテクチャ戦略策定
全行アーキ戦略（新CRM領域）
全行アーキ戦略PMO（情報系領域）
Food Transformation Exec Forum
データ・AI戦略検討
コーポレートバンキング・国際業務
海外コアバンキングシステム導入（中国）
Microsoft Office365導入拡大
ご支援実績
法人チャネル移行対応
法人・リテール
住宅ローンBPR
次期カスタマーセンター計画策定
BaaSプラットフォーム構築
デジタルサービス
AI業務適用技術POC等推進
CoE計画策定・推進（PEGA/RPA）
システム人材中途採用強化
SDG/ESG関連新規事業創出
PJ Symphony対応（米国）
デジタルファクトリー（SFDC）
AI Powered Enterprise Value Cockpit導入
ITSM導入拡大（ServiceNow）
生成AI推進PT
貴行次期CMS選定支援
サイバーセキュリティ領域における行員支援
新MUFG相続総合サービス
営業力強化プログラム
市場システムアーキプロセス実行支援及び運営支援
セキュリティアーキテクチャ検討
日銀決済支援
法人営業力強化プログラムグランドデザイン支援
GFCDテクノロジープログラム
ISO20022顧客移行支援
市場
グローバシステムグランドデザイン策定
サイバーセキュリティ推進
デジタルサービス
不変